## User stories (hidden)
User Stories
Groups | ID | As a... | I want/need ... | so that/because... | Additional Information | Story Point Estimation
1. Creating an account and logging in
2. Handling current share portfolio
3. Adding balance and purchasing shares
4. Security
5. Other

## Backlog Overall
ID | Task
1 | Build Database
2 | Link Web pages to database
3 | Import libarys and API's
4 | Create Log In/Registration Pages
5 | Create Dashboard
6 | Create share page
7 | Create settings page
8 | Create account information page
9 | Create buy/sell buttons
10 | Create candle stick charts
11 | Create line graphs
12 | Create check boxes for share graphs
13 | Implement PHP onto HTML
14 | Implement javascript into HTML
15 | Create forum for website
16 | Implement forum into website proper
17 | Create cascading style sheet for website internals
18 | Create leaderboard system
19 | Create interactive website via javascript after functionality is complete
20 | Create currency exchange page with all workings involved
21 | Build BOTS for website.
22 | Write algorithm for profit/loss margins of portfolio

## Product BacklogSprint Plan
ID | Item Priority | Item Description | Story Point Estimation | Velocity
1 | High | Create Log in page HTML only | 1 | 53
2 | High | Create Registration Page HTML only | 1 |  | Group Roles
3 | High | Create Share Page HTML only | 1 |  | Role | Assigned to
4 | High | Create Dashboard HTML only | 1 |  | Product Owner | Jung-Mo
5 | High | Generate cascading style sheet for current website internals | 2 |  | Scrum Master | Igor
6 | High | Select Shares to be implemented to be bought and sold | 1 |  | Team member 1 | Alex
7 | High | Create Javascript for login page functionality | 2 |  | Team member 2 | Emilio
8 | High | Create Javascript for registration functionality | 2
9 | High | Test functionality of login and registration pages after javascript implemented | 2
10 | High | look up a proper api for drawing graph and study methods | 2
11 | High | look up a proper api for checking stock market and study methods | 2 |  | Sprint 1
12 | High | implement graph and stock api on the html page | 3 |  | Plan |  |  | Rollover From Previous Sprint | Rollover Task Allocation
13 | High | set up codeigniter framework to ensure html and javascript is compatiable | 1 |  | Planned (ID) | Status | Task Allocation | N/A | N/A
14 | High | design basic framework structure with input from database and html so far | 5 |  | 1 | Complete | Alex | N/A | N/A
15 | High | write javascript/jquery functions for the html pages quantity * current price | 2 |  | 2 | Complete | Alex | N/A | N/A
16 | High | write javascript/jquery functions for the html pages check boxes for displaying monthly,weekly,daily graph | 4 |  | 3 | Complete | Igor | N/A | N/A
[5 empty] | 4 | Complete | Igor | N/A | N/A
17 | High | Testing on the functionality of model and controller to ensure it functions as needed | 1 |  | 5 | Complete | Alex | N/A | N/A
18 | High | Establish entities and attributes | 1 |  | 6 | Complete | Alex | N/A | N/A
19 | High | Refresh ERD and normalisation | 2 |  | 7 | Complete | Alex | N/A | N/A
20 | High | Create Entity Relationship Diagram | 1 |  | 8 | Complete | Alex | N/A | N/A
21 | High | Write queries and code for adding data to database via webpage | 4 |  | 9 | Complete | Alex | N/A | N/A
22 | High | Write code for querying database for user credentials | 2 |  | 10 | Complete | Jung-Mo | N/A | N/A
23 | High | Normalisation | 1 |  | 11 | Complete | Jung-Mo | N/A | N/A
24 | High | Draw up database schema diagram | 1 |  | 12 | Complete | Jung-Mo | N/A | N/A
25 | High | Create database and tables | 1 |  | 13 | Complete | Jung-Mo | N/A | N/A
26 | High | Populate database with dummy data for testing | 1 |  | 14 | Complete | Alex | N/A | N/A
27 | High | Write code to link db to webpage | 1 |  | 15 | Complete | Jung-Mo | N/A | N/A
28 | High | Create LSE page HTML only | 1 |  | 16 | Complete | Jung-Mo | N/A | N/A
29 | High | Create Leader Board page HTML only | 1 |  |  | Complete | Igor | N/A | N/A
30 | High | Create Settings page HTML only | 1 |  | 17 | Complete | Emilio | N/A | N/A
31 | High | Add button functionality to link all html pages | 1 |  | 18 | Complete | Emilio | N/A | N/A
32 | High | Create currency exchange page HTML only | 1 |  | 19 | Complete | Emilio | N/A | N/A
Goal Of First Sprint |  |  |  |  | 20 | Complete | Emilio | N/A | N/A
The goal of the first sprint is to lay the framework and foundations for all future construction of the project, this includes basic web pages and database aswell as java api implmentation. |  |  |  |  | 21 | Complete | Emilio | N/A | N/A
[5 empty] | 22 | Complete | Emilio | N/A | N/A
1 | High | Create Buy functionality for website | 4 | 71 | 23 | Complete | Emilio | N/A | N/A
2 | High | Create Sell functionality for website | 4 |  | 24 | Complete | Emilio | N/A | N/A
3 | High | Choose currencys to be used on the currency page | 1 |  | 25 | Complete | Emilio | N/A | N/A
4 | High | Implement portfolio table from the database | 3 |  | 26 | Complete | Emilio | N/A | N/A
5 | High | Implement portfolio graph for dashboard page | 5 |  | 27 | Complete | Igor | N/A | N/A
6 | High | Implement form validation for log in page | 2 |  | 28 | Complete | Igor | N/A | N/A
7 | High | Implement validation for registration page | 2 |  | 29 | Complete | Igor | N/A | N/A
8 | High | Implement leaderboards page | 5 |  | 30 | Complete | Alex | N/A | N/A
9 | High | Implement the currency exchange page | 5 |  | 31 | Complete | Igor | N/A | N/A
10 | High | Create alogrithm to calculate profit and loss based on currency fluctuations | 10 |  | 32 | Complete | Igor | N/A | N/A
11 | High | Implement profit loss colour coding for stock graphs | 1
12 | High | Implement settings page functionality | 3
13 | High | Add funds functionality to website | 2
14 | High | Add welcome message to dashboard upon logging in | 1
15 | High | Implement sales volume to website | 6
16 | High | Implement dynamic balance for website | 2
17 | High | Overhaul the look of the website | 4
18 | High | Implement transaction history | 5
19 | High | Change london stock exchange to new york stock exchange on website | 1
20 | High | Upgrade website UI to a higher standard for customer | 3
21 | High | Amend database structure | 2
Sprint 2
[5 empty] | Plan |  |  | Rollover From Previous Sprint | Rollover Task Allocation
[5 empty] | Planned (ID) | Status | Task Allocation | N/A | N/A
Goal Of Second Sprint |  |  |  |  | 1 | Complete | Igor | N/A | N/A
The goal of the second sprint is to finish the function of the website and by the end of this sprint the website will be fully functional with minimal bugs if any to fix in the next sprint. |  |  |  |  | 2 | Complete | Igor | N/A | N/A
[5 empty] | 3 | Complete | Alex | N/A | N/A
1 | High | Gain understanding of the Bootstrap framework | 6 | 90 | 4 | Complete | Jung-Mo | N/A | N/A
2 | High | Use Bootstrap to create a responsive website | 20 |  | 5 | Complete | Jung-Mo | N/A | N/A
3 | High | Complete balance transaction in the database | 2 |  | 6 | Complete | Igor | N/A | N/A
4 | High | Implement balance transaction to settings page | 2 |  | 7 | Complete | Igor | N/A | N/A
5 | High | Move Add funds from settings to a new window via the balance button | 3 |  | 8 | Complete | Jung-Mo | N/A | N/A
6 | High | Move update database buttons from dashboard to settings page for a better UI look | 1 |  | 9 | Complete | Alex | N/A | N/A
7 | High | Export transaction to an excel sheet external | 2 |  | 10 | Complete | Igor | N/A | N/A
8 | High | Implement algorithm to complete profit/loss graphs | 4 |  | 11 | Complete | Jung-Mo | N/A | N/A
9 | High | Implement Macro to automatically buy and sell at specified prices | 10 |  | 12 | Complete | Emilio | N/A | N/A
10 | High | Gain understanding on how to implement and create bots to use on the exchange | 20 |  | 13 | Complete | Emilio | N/A | N/A
11 | High | Implement bots using knowledge gathered in research | 20 |  | 14 | Complete | Alex | N/A | N/A
[5 empty] | 15 | Complete | Jung-Mo | N/A | N/A
[5 empty] | 16 | Complete | Emilio | N/A | N/A
[5 empty] | 17 | Complete | Alex | N/A | N/A
[5 empty] | 18 | Complete | Emilio | N/A | N/A
[5 empty] | 19 | Complete | Alex | N/A | N/A
[5 empty] | 20 | Complete | Alex | N/A | N/A
[5 empty] | 21 | Complete | Emilio | N/A | N/A
Goal Of Third Sprint
The goal of this final sprint is to complete all final objectives to ensure the website is fully functional and adheres to our customers specifications and all major bugs are reliably eliminated before handover can commence with the client. |  |  |  |  | Sprint 3
[5 empty] | Plan |  |  | Rollover From Previous Sprint | Rollover Task Allocation
Total Story Point Estimation: |  |  | 214 |  | Planned (ID) | Status | Task Allocation | N/A | N/A
|  | Note - 1 storypoint is equal to 1 hours work. |  |  | 1 | Complete | Alex/Igor | N/A | N/A
[5 empty] | 2 | Complete | Alex/Igor | N/A | N/A
[5 empty] | 3 | Complete | Emilio | N/A | N/A
[5 empty] | 4 | Complete | Emilio | N/A | N/A
[5 empty] | 5 | Complete | Emilio | N/A | N/A
[5 empty] | 6 | Complete | Emilio | N/A | N/A
[5 empty] | 7 | Complete | Emilio | N/A | N/A
[5 empty] | 8 | Complete | Jung-Mo | N/A | N/A
[5 empty] | 9 | Complete | Jung-Mo | N/A | N/A
[5 empty] | 10 | Complete | Jung-Mo | N/A | N/A
[5 empty] | 11 | Complete | Jung-Mo | N/A | N/A

## Sprint Backlog (Sprint 1)
Sprint Tasks |  |  | Days of the Sprint
Sprint 1 | Team Member | Story Points | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 17 | 18 | 19
Create Log in page HTML only | Alex | 1 | bar: Days of the Sprint 1
Create Registration Page HTML only | Alex | 1 | bar: Days of the Sprint 3
Create Share Page HTML only | Igor | 1 | bar: Days of the Sprint 4
Create Dashboard HTML only | Igor | 1 | bar: Days of the Sprint 6
Generate cascading style sheet for current website internals and add button functionality | Alex/Igor | 4 | bar: Days of the Sprint 9 to Days of the Sprint 10
Select Shares to be implemented to be bought and sold | Jung-Mo | 1 | bar: Days of the Sprint 8
Create Functionality via codeignitor | Alex | 2 | bar: Days of the Sprint 11 to Days of the Sprint 12
Test functionality of login and registration pages after implemented | Alex | 1 | bar: Days of the Sprint 16
look up a proper api for drawing graph and study methods | Jung-Mo | 1 | bar: Days of the Sprint 5
look up a proper api for checking stock market and study methods | Jung-Mo | 1 | bar: Days of the Sprint 5
implement graph and stock api on the html page | Jung-Mo | 6 | bar: Days of the Sprint 6 to Days of the Sprint 7; Days of the Sprint 10; Days of the Sprint 17 to Days of the Sprint 19
set up codeigniter framework to ensure html and javascript is compatiable | Jung-Mo | 1 | bar: Days of the Sprint 4; Days of the Sprint 11 to Days of the Sprint 14; Days of the Sprint 16
design basic framework structure with input from database and html so far | Everyone | 5 | bar: Days of the Sprint 15 to Days of the Sprint 16; Days of the Sprint 17 to Days of the Sprint 19
write javascript/jquery functions for the html pages quantity * current price | Jung-Mo | 2 | bar: Days of the Sprint 9; Days of the Sprint 19
write javascript/jquery functions for the html pages check boxes for displaying monthly,weekly,daily graph | Jung-Mo | 2 | bar: Days of the Sprint 16; Days of the Sprint 17
Testing on the functionality of model and controller to ensure it functions as needed | Igor | 1 | bar: Days of the Sprint 4
Establish entities and attributes | Emilio | 2 | bar: Days of the Sprint 5; Days of the Sprint 7
Refresh ERD and normalisation | Emilio | 2 | Days of the Sprint 8: 2
Create Entity Relationship Diagram | Emilio | 1 | bar: Days of the Sprint 7
Write queries and code for adding data to database via webpage | Emilio | 2 | bar: Days of the Sprint 9; Days of the Sprint 11
Write code for querying database for user credentials | Emilio | 2
Normalisation | Emilio | 1 | bar: Days of the Sprint 12
Draw up database schema diagram | Emilio | 1 | bar: Days of the Sprint 12
Create database and tables | Emilio | 2 | bar: Days of the Sprint 5; Days of the Sprint 7
Populate database with dummy data for testing | Emilio | 1 | bar: Days of the Sprint 12
Write Codeignitor models | Emilio | 2 | Days of the Sprint 16: 2
Write code to link db to webpage | Emilio | 2 | bar: Days of the Sprint 12
Create LSE page HTML only | Igor | 1 | bar: Days of the Sprint 10
Create Leader Board page HTML only | Igor | 1 | bar: Days of the Sprint 11
Create Settings page HTML only | Igor | 1 | bar: Days of the Sprint 2
Create currency exchange page HTML only | Igor | 1 | bar: Days of the Sprint 15
| Total | 53 | 52 | 51 | 50 | 47 | 43 | 41 | 37 | 34 | 31 | 28 | 24 | 18 | 17 | 16 | 14 | 8 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 0
Students should record how many velocity points they worked on a task or how many are remaining for each task; they should then update the total as well. The total row would reach to zero when all tasks are completed.

## Sprint 1 Retrospective
Sprint 1 Retrospective
We regularly met up in the university library to conplete the work needed for this sprint, we held regular meetings via discord and kept in communication through our whatsapp group this proved very efficent in regards to team management, our team continued to use gitlab in order to ensure we have good version control and no mistakes are made permanent from an accidential overwrite. We have decided based on evidence from sprint 1 to continue the use of gitlab as it has proven to be very useful in regards to the handling of our project data so we will use this tool in the future. We assigned the work based upon what the team agreed to take on and as such we ended up with a very efficent sprint because of this, we split the work into sections and using the story point estimation worked out how best to complete the work. We also used branch merging via git to develop and consolidate the database and website, we however found this to be very time consuming and overall not worth the amount of effort put into the merging to warrant continuing to use this in further sprints. We all have decided to once every end of the day to pull the repository of the gitlab in order to prevent any mishaps and ensure we are all working on the same version of files.

## Sprint 1 Review
Sprint 1 Review
Challenges faced by our team included the decision to switch to using codeignitor for the website and attempting to divide the programming jobs between the team members due to the lack of experience at team collaboration in regards to programming this caused a slight slowdown in the work output as the team adjusted to this new way of working, a major problem we faced was that the customer was not happy with the scope of our initial pitch and because of this we needed to expand the scope considerably which we then doubled out story point estimation from what was originally planned. Database creation was completed on time however while the creation of the database held no problems the migration of the database onto the raptor server proved more diffciult then we anticipated, this meant that it took a whole day of work to migrate the database over but was completed on time for the completion of sprint 1 in the end, overall the database creation had no major problems this sprint. Javascript/API we used the alpha vantage API to return the JSON data to the server and we also used the google chart API to generate the graphs for our website, The implementation of these API's and the rest of the javascript was no issue whatsoever and was completed on time and on schedule. HTML/CSS construction was completed to a good standard in the time span we specified before commencing this sprint, the connection of webpages to each other took very little time to achieve and as such testing of codeignitor could commence, however we ran into a issue with attempting to test the website and its functions due to the way codeignitor is configured we solved this issue but merging branches via git and now we can access the website from a single link. Every friday our team held an inperson meeting with eachother in order to ensure the documentation was up to date and everyone knew what they needed to complete and what was already complete, in short we completed all objectives assigned to us for the first sprint and completed some tertiary objectives that the customer reccomended to us during our meetings this includes our exchange page overall our team is in agreement that sprint 1 was a complete success.

## Sprint Backlog (Sprint 2)
Sprint Tasks |  |  | Days of the Sprint
Sprint 2 | Team Member | Story Points | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 17 | 18
Create Buy functionality for website | Igor | 4 | Days of the Sprint 10: 2; Days of the Sprint 11: 2
Create Sell functionality for website | Igor | 4 | Days of the Sprint 10: 2; Days of the Sprint 11: 2
Choose currencys to be used on the currency page | Alex | 1 | bar: Days of the Sprint 10
Implement portfolio table from the database | Jung-Mo | 3 | bar: Days of the Sprint 11 to Days of the Sprint 13
Implement portfolio graph for dashboard page | Jung-Mo | 5 | Days of the Sprint 11: 2; Days of the Sprint 12: 2; Days of the Sprint 13: 1
Implement form validation for log in page | Igor | 2 | Days of the Sprint 13: 2
Implement validation for registration page | Igor | 2 | Days of the Sprint 14: 2
Implement leaderboards page | Jung-Mo | 5 | Days of the Sprint 18: 5
Implement the currency exchange page | Alex | 5 | bar: Days of the Sprint 11 to Days of the Sprint 15
Create alogrithm to calculate profit and loss based on currency fluctuations | Igor | 10 | Days of the Sprint 11: 2; Days of the Sprint 12: 2; Days of the Sprint 13: 2; Days of the Sprint 14: 2; Days of the Sprint 15: 2
Implement profit loss colour coding for stock graphs | Jung-Mo | 1 | bar: Days of the Sprint 16
Implement settings page functionality | Emilio | 3 | bar: Days of the Sprint 14 to Days of the Sprint 16
Add funds functionality to website | Emilio | 2 | bar: Days of the Sprint 15 to Days of the Sprint 16
Add welcome message to dashboard upon logging in | Alex | 1 | bar: Days of the Sprint 16
Implement sales volume to website | Jung-Mo | 6 | Days of the Sprint 16: 3; Days of the Sprint 17: 3
Implement dynamic balance for website | Emilio | 2 | bar: Days of the Sprint 16; Days of the Sprint 17
Overhaul the look of the website | Alex | 4 | bar: Days of the Sprint 14 to Days of the Sprint 16; Days of the Sprint 17
Implement transaction history | Emilio | 5 | bar: Days of the Sprint 13 to Days of the Sprint 16; Days of the Sprint 17
Change london stock exchange to new york stock exchange on website | Alex | 1 | bar: Days of the Sprint 16
Upgrade website UI to a higher standard for customer | Alex | 3 | bar: Days of the Sprint 16; Days of the Sprint 17 to Days of the Sprint 18
Amend database structure | Emilio | 2 | bar: Days of the Sprint 14 to Days of the Sprint 15
| Total | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 66 | 56 | 50 | 42 | 33 | 25 | 13 | 0 | 0 | 0 | 0 | 0 | 6 | 0
Students should record how many velocity points they worked on a task or how many are remaining for each task; they should then update the total as well. The total row would reach to zero when all tasks are completed.

## Sprint 2 Retrospective
Sprint 2 Retrospective
For sprint 2 we mainly continued to use the forms of communication that we used during sprint 1 however this time we increased the amount of meetings and all pulled from the git repository more regularly as to ensure we had the same data and did not overwrite any work accidently, as specified during our sprint 1 retrospective we did not do any branch merging into master this time and because of this we saved significant time in our version control and it also allowed us to increase or efforts into the more functional parts of the website such as getting the graphs and buying and selling ready for the end of the sprint which was a complete success, story point estimation turned out to be to the same level we expected from sprint 1 and as such we added a lot more onto sprint to due to our confidence that we could complete 45% more then we completed last sprint due to all of the main functionalities working as intended, the team member Alex Collins had to spend some time relearning how CodeIgniter works as he last used it 3 years ago and had become rusty.

## Sprint 2 Review
Sprint 2 Review
The challenges we faced during this sprint was needing to implement the database and website together into a workable site, we did however complete this with the use of PHP and SQL to ensure the website functions as intended, we have also grown accustomed to working with each other and group coding during this sprint so output during this sprint was much higher than our previous sprint due to this adjustment, as per our customers request the whole UI was updated and overhauled to bring it to a much nicer standard and is more intuitive then before for the user, we utilised a variety of algorithms to create the buy and sell share system that we have now fully implemented during this sprint and testing shows it works very well as we expected, Database is now fully implemented into the website an tested to show its robustness all the main features involving the website has been finished in this sprint and tested as well, we have also constructed the leader boards page as per the customers wishes but need to complete the internals of it as right now it is a placeholder of sorts, overall the whole sprint 2 went incredibly well and was much more efficient then sprint 1 we hope to improve on this for our final sprint in sprint 3 to not only reach our goal but exceed it, due to time constraints of other projects we had to condense down the sprint in half relative to work and this can be seen in our burndown chart however all work is done to a good standard and completed regardless we worked extra hours to achieve this goal.

## Sprint Backlog (Sprint 3)
Sprint Tasks |  |  | Days of the Sprint
Sprint 3 | Team Member | Story Points | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 17 | 18 | 19
Gain understanding of the Bootstrap framework | Alex/Igor | 6 | Days of the Sprint 2: 2; Days of the Sprint 4: 2; Days of the Sprint 6: 2
Create a responsive and aesthetically pleasing website via CSS | Alex/Igor | 20 | 2 |  | 2 |  | 2 |  | 2 |  | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
Complete balance transaction in the database | Emilio | 2 | bar: Days of the Sprint 18 to Days of the Sprint 19
Implement balance transaction to settings page | Emilio | 2 | bar: Days of the Sprint 5; Days of the Sprint 19
Move Add funds from settings to a new window via the balance button | Emilio | 3 | Days of the Sprint 6: 3
Move update database buttons from dashboard to settings page for a better UI look | Emilio | 1 | bar: Days of the Sprint 8; Days of the Sprint 19
Export transaction to an excel sheet external | Emilio | 2 | bar: Days of the Sprint 9
Implement algorithm to complete profit/loss graphs | Jung-Mo | 4 | bar: Days of the Sprint 1 to Days of the Sprint 4
Implement Macro to automatically buy and sell at specified prices | Jung-Mo | 10 | bar: Days of the Sprint 8 to Days of the Sprint 11; Days of the Sprint 14 to Days of the Sprint 16; Days of the Sprint 17 to Days of the Sprint 19
Gain understanding on how to implement and create bots to use on the exchange | Jung-Mo | 20 | Days of the Sprint 1: 3; Days of the Sprint 3: 3; Days of the Sprint 5: 3; Days of the Sprint 7: 3; Days of the Sprint 9: 3; Days of the Sprint 11: 3; Days of the Sprint 12: 2
Implement bots using knowledge gathered in research | Jung-Mo | 20 | Days of the Sprint 2: 2; Days of the Sprint 4: 2; Days of the Sprint 6: 2; Days of the Sprint 8: 2; Days of the Sprint 10: 2; Days of the Sprint 12: 2; Days of the Sprint 14: 2; Days of the Sprint 16: 2; Days of the Sprint 18: 2; Days of the Sprint 19: 2
| Total | 90 | 84 | 79 | 73 | 68 | 62 | 55 | 50 | 46 | 39 | 35 | 30 | 25 | 24 | 20 | 18 | 14 | 0 | 0 | 0 | 0 | 0 | 12 | 7 | 0
Students should record how many velocity points they worked on a task or how many are remaining for each task; they should then update the total as well. The total row would reach to zero when all tasks are completed.

## Sprint 3 Retrospective
Sprint 3 Retrospective
Our ability to work as a team was pushed to the very limit with the need to socially distance, 2 of our members live from home and as such needed to use the vpn network from home which caused minor issues and required us to delegate work based on what was best feasible for the group member, after some trial and error this worked out well and we got back on track with our work, we decided to increase meetings to 3 a week in order to make sure we all not only understood our work that needed to be done but also to ensure we could keep the sprint chart and backlog updated regularly, overall if we could improve on this sprint we would have increased our meetings by 1 more in order to be help eachother with the fact we could not speak to eachother in person, the use of discord to meet in our own provate server aided us greatly in creating an enviorment in which we could ask eachother questions and help in answering them, overall we would definitly use discord from the start if we was to do this project again.

## Sprint 3 Review
Sprint 3 Review
The coronavirus situation was a major factor in some aspects of the project having to be scrapped, one noticeable example is instead of many bots we could only do one due to issues in regard to assessing the universities network from home, this also meant that all work was done away from each other, to compensate for this we tripled the amount of meetings per week to ensure we stayed on the correct path and did not deviate from our final sprint objectives, we decided after analysing the software to abandon bootstrap to aid in our website due to bootstrap being ill suited for our needs and instead opted to simply improve the CSS for our website instead, overall we completed all the objectives we set for ourselves and only failed on some of the tertiary objectives due to time constraints and lack of expertise necessary to do them in time however all objectives that were needed to be met have been met efficiently and on time and the customer will no doubt be happy with the results.

## FunctionalNonFunctional Requirm (hidden)
Requirements
Functional Requirments | Non-Functional Requirements

## Knowledge acquisition tasks (hidden)
LIST OF KNOWLEDGE ACQUISITION TASKS
Item number | Item Description
1 | How to create a database in order to store all of the necessary details. For example learn SQL and other techniques
2 | Learn API needed to create graphs for website
3
4
5
6
7
8
9
10
11

## References (hidden)
REFERENCES